## Phase 1 - Master schedule (hidden)
7 Sprint: 27/03/25 - 20/01/26 | [10 empty] | 2 | [7 empty] | 3
Category | Module | UC | Task | Priority | Sprint | Note | BA Team |  |  |  | BE team |  |  |  | FE team |  |  |  | Python Team
[7 empty] | PIC | Deadline | Actual deadline | Status | PIC | Deadline | Actual deadline | Status | PIC | Deadline | Actual deadline | Status | PIC | Deadline | Actual deadline | Status
User site
Security & Compliance |  |  |  | Highest | All sprints |  |  |  |  | Inprogress, Done WF, Inreview Document | huynh.vu | 2025-11-14 |  | Todo
Multilang support |  |  |  | Highest | All sprints | File: Multiple language | Anh.nguyen75 | 2025-12-08 |  |  |  | 2025-12-12 |  | Todo | quang.do | 2025-12-12 |  | inprogress
[UC-C-00] Navigation Bar & Header |  |  |  | Medium | Sprint 1 |  | Long.ngo | 2025-10-23 | [5 empty] | Todo | nam.truong | 2025-10-23 |  | Done
Landing Page | [UC-C-01] Landing Page |  | View landing page | Highest | Sprint 1 |  | Long.ngo | 2025-10-31 |  |  | quyet.nguyen4 | 2025-11-07 |  | Todo | thao.dong3 | 2025-11-07 |  | Ready for test
Authentication & KYC | [UC-C-02] Authentication | [UC-C-02.1] Log In | - User registration - Sumsub integration - Email verification | Highest | Sprint 1 |  | Mai.nguyen14 | 2025-10-31 |  |  | quyet.nguyen4 | 2025-11-07 |  | Ready for test | tung.pham | 2025-11-07 |  | Ready for test
|  | [UC-C-02.2] Registration |  | Highest | Sprint 1 |  | Mai.nguyen14 | 2025-10-31 |  |  | huynh.vu | 2025-11-07 |  | Ready for test | tung.pham | 2025-11-07 |  | Ready for test
Profile Management | [UC-S-01] Profile Management | [UC-S-01.1] View Profile | Allow startup to view their own profile | Highest | Sprint 1 |  | Mai.nguyen14 | 2025-11-05 |  |  | huynh.vu | 2025-11-17 |  | inprogress | quang.do | 2025-11-20 |  | inprogress
|  | [UC-S-01.2] Edit Profile | Allow startup to edit their profile: - Business plans - Financial plans - Team information - Traction | Highest | Sprint 1 |  | Mai.nguyen14 | 2025-11-05 |  |  | huynh.vu | 2025-11-17 |  | inprogress | quang.do | 2025-11-21 |  | inprogress
|  | [UC-S-01.3] Profile Privacy Settings | Allow startup to block, restrict, or manage profile visibility and communications | Highest | Sprint 1 |  | Mai.nguyen14 | 2025-11-05 |  |  | huynh.vu | 2025-11-17 |  | inprogress | quang.do | 2025-11-21 |  | inprogress
| [UC-I-01] Profile Management | [UC-I-01.1] View Profile | Allow investor to view their own profile | Highest | Sprint 1 |  | Anh.nguyen75 | 2025-11-05 |  |  | quyet.nguyen4 | 2025-11-17 |  | inprogress | quang.do, thao.dong3 | 2025-11-21 |  | inprogress
|  | [UC-I-01.2] Edit Profile | Allow investor to edit their profile: - investment thesis - portfolio - criteria | Highest | Sprint 1 |  | Anh.nguyen75 | 2025-11-05 |  |  | quyet.nguyen4 | 2025-11-17 |  | inprogress | thao.dong3 | 2025-11-21 |  | inprogress
|  | [UC-I-01.3] Profile Privacy Settings | Allow investor to block, restrict, or manage profile visibility and communications | Highest | Sprint 1 |  | Anh.nguyen75 | 2025-11-05 |  |  | quyet.nguyen4 | 2025-11-17 |  | inprogress | thao.dong3 | 2025-11-21 |  | inprogress
Dashboard | [UC-S-02] Startup Dashboard | [UC-S-02] Startup Dashboard | Allow investor to view dashboard on: - Upcoming calls or meetings with startups - Notifications on new connection requests - Charts showing engagement metrics (e.g., startups contacted, deals in each stage) | Highest | Sprint 3 |  | Anh.nguyen75 | 2025-11-27 |  | Not start | quyet.nguyen4 | 2025-12-01 |  | Todo |  | 2025-12-03
| [UC-I-02] Investor Dashboard | [UC-I-02] Investor Dashboard | Allow investor to view dashboard on: - Upcoming calls or meetings with startups - Notifications on new connection requests - Charts showing engagement metrics (e.g., startups contacted, deals in each stage) | Highest | Sprint 3 |  | Mai.nguyen14 | 2025-11-28 |  | Not start | quyet.nguyen4 | 2025-12-02 |  | Todo |  | 2025-12-05
Discovery | [UC-S-03] Investor Discovery | [UC-S-03.1]. Explore Start-ups | Allow startup to view the list of recommended matching investors | Highest | Sprint 2, Sprint 1 |  | Mai.nguyen14 | 2025-11-13 |  |  | huynh.vu | 2025-11-19 |  | Todo | huy.du | 2025-11-25 |  | inprogress
|  |  | Allow startup to filter investors by criteria such as sector, geography, investment stage, ticket size, and investor type (VC, angel, corporate, etc.). |  | Sprint 2, Sprint 1 |  |  | 2025-11-13 |  |  | huynh.vu | 2025-11-19 |  | Todo | huy.du | 2025-11-25 |  | inprogress
|  | [UC-S-03.2]. View Start-ups Profile | Allow startup to view detailed investor profiles, including portfolio, investment thesis, focus sectors, average investment size, and team members. | Highest | Sprint 2 |  | Mai.nguyen14 | 2025-11-13 |  |  | huynh.vu | 2025-11-19 |  | Todo | huy.du | 2025-11-25 |  | Todo
|  |  | Allow startup to send connection request to investor |  | Sprint 2 |  |  | 2025-11-13 |  |  | huynh.vu | 2025-11-19 |  | Todo | huy.du | 2025-11-25 |  | Todo
| [UC-I-03] Startup Discovery | [UC-I-03.1]. Explore Investor | Allow investor to view the list of recommended matching startups | Highest | Sprint 2, Sprint 1 |  | Anh.nguyen75 | 2025-11-13 |  |  | huynh.vu | 2025-11-20 |  | Todo | huy.du | 2025-11-26 |  | Todo
|  |  | Allow investor to manually filter and search startups by criteria such as sector, location, stage, traction, and fundraising amount. |  | Sprint 1, Sprint 2 |  |  | 2025-11-13 |  |  | huynh.vu | 2025-11-20 |  | Todo | huy.du | 2025-11-26 |  | Todo
|  | [UC-I-03.2]. View Investor Profile | Allow investor to view detailed startup profiles, including: - business plan - traction - team - financials - fundraising information - performance report | Highest | Sprint 2 |  | Anh.nguyen75 | 2025-11-13 |  |  | huynh.vu | 2025-11-20 |  | Todo | huy.du | 2025-11-26 |  | Todo
|  |  | Allow investor to send a connection request to startups |  | Sprint 2 |  |  | 2025-11-13 |  |  | huynh.vu | 2025-11-20 |  | Todo | huy.du | 2025-11-26 |  | Todo
Connection Management | [UC-S-04] Connection Management | [UC-S-04.1] Connection List |  | High | Sprint 2 |  | Anh.nguyen75 | 2025-11-13 |  |  | quyet.nguyen4 | 2025-11-18 |  | Todo | dai.doan | 2025-11-25 |  | Todo
|  | [UC-S-04.2] Connection Details |  | High | Sprint 2 |  | Anh.nguyen75 | 2025-11-13 |  |  | quyet.nguyen4 | 2025-11-19 |  | Todo | dai.doan | 2025-11-25 |  | Todo
| [UC-I-04] Connection Management | [UC-I-04.1] Connection List |  | High | Sprint 2 |  | Mai.nguyen14 | 2025-11-13 |  |  | quyet.nguyen4 | 2025-11-18 |  | Todo | dai.doan | 2025-11-25 |  | Todo
|  | [UC-I-04.2] Connection Details |  | High | Sprint 2 |  | Mai.nguyen14 | 2025-11-13 |  |  | quyet.nguyen4 | 2025-11-19 |  | Todo | dai.doan | 2025-11-25 |  | Todo
Deal Management & Docsend or Signit.sa Integration | [UC-S-05] Deal Room | [UC-S-05.1] Deal Room List |  | High | Sprint 2, Sprint 3 |  | Anh.nguyen75 | 2025-11-27 |  | Not start | huynh.vu | 2025-11-21 |  | Todo | thao.dong3 | 2025-11-24 |  | Todo
|  | [UC-S-05.2] Deal Room Details |  | High | Sprint 2, Sprint 3 |  | Anh.nguyen75 | 2025-11-27 |  | Not start | huynh.vu | 2025-11-24 |  | Todo | thao.dong3 | 2025-12-01 |  | Todo
| [UC-I-05] Deal Room | [UC-I-05.1] Deal Room List |  | Highest | Sprint 2, Sprint 3 |  | Mai.nguyen14 | 2025-11-27 |  | Not start | huynh.vu | 2025-11-24 |  | Todo | thao.dong3 | 2025-11-24 |  | Todo
|  | [UC-I-05.2] Deal Room Details |  | Highest | Sprint 2, Sprint 3 |  | Mai.nguyen14 | 2025-11-27 |  | Not start | huynh.vu | 2025-11-25 |  | Todo | thao.dong3 | 2025-12-01 |  | Todo
Performance Reporting Management | [UC-S-06] Performance Reporting | [UC-S-06] Performance Reporting |  | High | Sprint 3 |  | Long.ngo | 2025-11-26 |  | Not start | quyet.nguyen4 | 2025-12-04 |  | Todo | quang.do | 2025-12-10 |  | Todo
Content Management/ Educational Blog | [UC-C-03] Educational Blog | [UC-C-03.1] Blog List |  | Medium | Sprint 5 |  | Long.ngo | [6 empty] | Todo |  |  |  | Todo
|  | [UC-C-03.2] Blog Details |  | Medium | Sprint 5 |  | Long.ngo | [6 empty] | Todo |  |  |  | Todo
Messaging System | [UC-C-03] Messaging System | [UC-C-03.1] View Conversation List | Allow users (startup or investor) to view all active conversations sorted by most recent activity, showing name, profile, and last message preview. | High | Sprint 2 |  | Mai.nguyen14 | [6 empty] | Todo |  |  |  | Todo
|  | [UC-C-03.2] Message Details | Allow users to initiate a chat once a connection request has been accepted (either direction). | High | Sprint 2 |  | Mai.nguyen14 | [6 empty] | Todo |  |  |  | Todo
|  |  | Allow users to send and receive text messages in real time through integrated chat | [10 empty] | Todo |  |  |  | Todo
Document Management | [M-UC-C-02] Document Management | [M-UC-C-02.1] Document List | Allow user to view a list of all documents they have uploaded, with details such as file name, upload date, and access status | Medium | Sprint 4 |  | Long.ngo | [6 empty] | Todo |  |  |  | Todo
|  |  | Allow user to upload documents (e.g., pitch deck, financial report, legal files) to the platform/delete uploaded documents |  | Sprint 4 | [8 empty] | Todo |  |  |  | Todo
|  |  | Allow user to set access permissions for each uploaded document — defining how long a document can be viewed |  | Sprint 4 | [8 empty] | Todo |  |  |  | Todo
|  | [M-UC-C-02.2] Document Details | Allow user to view document metadata and preview or download the file if access is granted. | Medium | Sprint 4 |  | Long.ngo | [6 empty] | Todo |  |  |  | Todo
Meeting Schedule Management |  |  |  | High | Sprint 3 |  | Long.ngo |  |  | Not start | quyet.nguyen4 | 2025-12-08 |  | Todo | quang.do | 2025-12-12 |  | Todo
WhatsApp Basic Integration | [UC-C-06] WhatsApp Reminders & Marketing | [UC-C-06.1] WhatsApp Reminders |  | Medium | Sprint 5 |  | Mai.nguyen14 | [6 empty] | Todo |  |  |  | Todo
|  | [UC-C-06.2] WhatsApp Automation Marketing |  | Medium | Sprint 5 |  | Mai.nguyen14 | [6 empty] | Todo |  |  |  | Todo
Matching System |  |  |  | Highest | Sprint 2, Sprint 3 |  | Mai.nguyen14 | 2025-11-24 |  | Not start | huynh.vu |  |  | Todo |  |  |  | Todo | phong.vu |  |  | inprogress
Mobile App
Common |  |  | Setup source base | Highest | Sprint 1 | [8 empty] | Todo | nam.truong |  |  | Done
Authentication & KYC Integration | [M-UC-C-01] Authentication | [M-UC-C-01.1] Log In |  | Highest | Sprint 1 |  | Long.ngo | 2025-11-06 | [5 empty] | Todo | nam.truong |  |  | Ready for test
|  | [M-UC-C-01.2] Registration |  | Highest | Sprint 1 |  | Long.ngo | 2025-11-06 | [5 empty] | Todo | nam.truong |  |  | Ready for test
Dashboard | [M-S-02] Startup Dashboard | [M-S-02] Startup Dashboard |  | High | Sprint 3 |  | Anh.nguyen75 |  |  | Not start | quyet.nguyen4 | 2025-12-01 |  | Todo | tung.pham | 2025-12-03 |  | Todo
| [M-I-02] Investor Dashboard | [M-I-02] Investor Dashboard |  | High | Sprint 3 |  | Mai.nguyen14 |  |  | Not start | quyet.nguyen4 | 2025-12-02 |  | Todo | tung.pham | 2025-12-04 |  | Todo
Profile Management | [M-UC-I-01] Profile Management | [M-UC-I-01.1] View Profile |  | Highest | Sprint 2 |  | Long.ngo | 2025-11-18 | [5 empty] | Todo | tung.pham | 2025-11-20 |  | inprogress
|  | [M-UC-I-01.2] Edit Profile |  | Highest | Sprint 2 |  | Long.ngo | 2025-11-18 | [5 empty] | Todo | tung.pham | 2025-11-20 |  | inprogress
|  | [M-UC-I-01.3] Profile Privacy Settings |  | Highest | Sprint 2 |  | Long.ngo | 2025-11-18 | [5 empty] | Todo | tung.pham | 2025-11-20 |  | inprogress
| [M-UC-S-01] Profile Management | [M-UC-S-01.1] View Profile |  | Highest | Sprint 2 |  | Long.ngo | 2025-11-20 | [5 empty] | Todo | tung.pham | 2025-11-21 |  | inprogress
|  | [M-UC-S-01.2] Edit Profile |  | Highest | Sprint 2 |  | Long.ngo | 2025-11-20 | [5 empty] | Todo | tung.pham | 2025-11-21 |  | inprogress
|  | [M-UC-S-01.3] Profile Privacy Settings |  | Highest | Sprint 2 |  | Long.ngo | 2025-11-20 | [5 empty] | Todo | tung.pham | 2025-11-24 |  | inprogress
Discovery | [M-UC-I-03] Investor Discovery | [M-UC-I-03.1]. Explore Start-ups |  | High | Sprint 2 |  | Mai.nguyen14 | 2025-11-20 | [5 empty] | Todo | nam.truong | 2025-11-24 |  | Todo
|  | [M-UC-I-03.3]. View Start-ups Profile |  | High | Sprint 2 |  | Mai.nguyen14 | 2025-11-20 | [5 empty] | Todo | nam.truong | 2025-11-25 |  | Todo
| [M-UC-S-03] Startup Discovery | [M-UC-S-03.1]. Explore Start-ups |  | High | Sprint 2 |  | Mai.nguyen14 | 2025-11-24 | [5 empty] | Todo | nam.truong | 2025-11-26 |  | Todo
|  | [M-UC-S-03.3]. View Start-ups Profile |  | High | Sprint 2 |  | Mai.nguyen14 | 2025-11-24 | [5 empty] | Todo | nam.truong | 2025-11-26 |  | Todo
Connection Management | [M-UC-I-04] Connection Management | [M-UC-I-04.1] Connection List |  | High | Sprint 2 |  | Mai.nguyen14 | 2025-11-21 | [5 empty] | Todo | nam.truong | 2025-11-27 |  | Todo
|  | [M-UC-I-04] Connection List |  | High | Sprint 2 |  | Mai.nguyen14 | 2025-11-21 | [5 empty] | Todo | nam.truong | 2025-11-27 |  | Todo
| [M-UC-S-04] Connection Management | [M-UC-S-04.1] Connection List |  | High | Sprint 2 |  | Anh.nguyen75 | 2025-11-25 | [5 empty] | Todo | nam.truong | 2025-11-27 |  | Todo
|  | [M-UC-S-04] Connection List |  | High | Sprint 2 |  | Anh.nguyen75 | 2025-11-25 | [5 empty] | Todo | nam.truong | 2025-11-27 |  | Todo
Investment Process | [M-UC-I-05] Deal Room | [M-UC-I-05.1] Deal Room List |  | High | Sprint 3 |  | Mai.nguyen14 |  |  | Not start | huynh.vu | 2025-11-21 |  | Todo | nam.truong | 2025-12-01 |  | Todo
|  | [M-UC-I-05.2] Deal Room Details |  | High | Sprint 3 |  | Mai.nguyen14 |  |  | Not start | huynh.vu | 2025-11-24 |  | Todo | nam.truong | 2025-12-04 |  | Todo
| [M-UC-S-05] Deal Room | [M-UC-S-05.1] Deal Room List |  | High | Sprint 3 |  | Anh.nguyen75 |  |  | Not start | huynh.vu | 2025-11-24 |  | Todo | nam.truong | 2025-12-01 |  | Todo
|  | [M-UC-S-05.2] Deal Room Details |  | High | Sprint 3 |  |  |  |  | Not start | huynh.vu | 2025-11-25 |  | Todo | nam.truong | 2025-12-04 |  | Todo
| [M-UC-C-04] Meeting Schedule |  |  | High | Sprint 3 |  | Anh.nguyen75 |  |  | Not start | huynh.vu | 2025-11-26 |  | Todo | nam.truong | 2025-12-04 |  | Todo
| Calendly Integration |  |  | High | Sprint 3 |  | Mai.nguyen14 |  |  | Not start | huynh.vu | 2025-11-27 |  | Todo | nam.truong | 2025-12-04 |  | Todo
Chat Integration | [M-UC-C-02] Messaging System | [M-UC-C-02.1] View Conversation List |  | High | Sprint 3 |  | Mai.nguyen14 | 2025-12-02 |  | Not start | huynh.vu | 2025-12-03 |  | Todo | thao.dong3 | 2025-12-05 |  | Todo
|  | [M-UC-C-02.2] Message Details |  | High | Sprint 3 |  | Mai.nguyen14 | 2025-12-02 |  | Not start | huynh.vu | 2025-12-04 |  | Todo | thao.dong3 | 2025-12-09 |  | Todo
Document Sharing | [M-UC-C-03] Document Management | [M-UC-C-03.1] Document List |  | High | Sprint 4 |  | Mai.nguyen14 | [6 empty] | Todo |  |  |  | Todo
|  | [M-UC-C-03.2] Document Deatails |  | High | Sprint 4 |  | Mai.nguyen14 | [6 empty] | Todo |  |  |  | Todo
Push Notifications |  |  |  | Medium | Sprint 4 |  | Long.ngo | [6 empty] | Todo |  |  |  | Todo
WhatsApp Integration |  |  |  | Medium | Sprint 4 |  | Long.ngo | [6 empty] | Todo |  |  |  | Todo
Admin site
Authentication | [UC-AD-01] Authentication | [UC-AD-01] Authentication | Log In | Highest | Sprint 1 |  | Mai.nguyen14 | 2025-10-31 | [5 empty] | Todo |  |  |  | Todo
|  |  | Log out | Highest | Sprint 1 |  | Mai.nguyen14 | 2025-10-31 | [5 empty] | Todo |  |  |  | Todo
Admin management | [UC-AD-02] Admin management | [UC-AD-02] Admin management |  | High | Sprint 2 |  | Mai.nguyen14 | 2025-10-31 |  |  | quyet.nguyen4 | 2025-11-20 |  | Todo | huy.du | 2025-11-21 |  | inprogress
Admin Dashboard | [UC-AD-03] User Management | [UC-AD-03.1] User List | - view list user - Ban user - Unban user | High | Sprint 2 |  | Anh.nguyen75 | 2025-11-14 |  |  | quyet.nguyen4 | 2025-11-21 |  | Todo | huy.du | 2025-11-25 |  | Todo
|  | [UC-AD-03.2] User Details | - view detail user | High | Sprint 2 |  | Anh.nguyen75 | 2025-11-14 |  |  | quyet.nguyen4 | 2025-11-24 |  | Todo | huy.du | 2025-11-25 |  | Todo
|  | [UC-AD-03.3] KYC AI Screening Criteria | Approve Investor/Entrepreneur KYC | Highest | Sprint 2 |  | Long.ngo | 2025-11-14 |  |  | huynh.vu | 2025-11-27 |  | Todo | huy.du | 2025-11-28 |  | Todo
| [UC-AD-04] Analytics Dashboard | [UC-AD-04] Analytics Dashboard | Analytics of which part? (Number of verify Investor/Entrepreneur, Number of submit KYC etc...) | High | Sprint 3 |  | Long.ngo |  |  | Not start | huynh.vu | 2025-12-09 |  | Todo | huy.du | 2025-12-11 |  | Todo
| [UC-AD-05] Deal Room Management | [UC-AD-05.1] Deal Room List | Admin Data Room Template Management | High | Sprint 3 |  | Long.ngo |  |  | Not start | huynh.vu | 2025-12-10 |  | Todo | huy.du | 2025-12-12 |  | Todo
|  | [UC-AD-05.2] Deal Room Details | Deal Room Dashboard | High | Sprint 3 |  | Long.ngo |  |  | Not start | quyet.nguyen4 | 2025-12-10 |  | Todo | huy.du | 2025-12-12 |  | Todo
CMS | [UC-AD-06] CMS |  | Create/Manage/Adjust Content | High | Sprint 4 |  | Long.ngo | [6 empty] | Todo |  |  |  | Todo

## Copy of Phase 1 - Master schedu (hidden)
7 Sprint: 27/03/25 - 20/01/26 | [16 empty] | 2 | [7 empty] | 3
Category | Module | UC | Task | Priority | Sprint | Note | BA Team | [9 empty] | BE team |  |  |  | FE team |  |  |  | Python Team
[7 empty] | Wireframe |  |  |  | Document |  |  | Design
[7 empty] | PIC | Deadline | Actual deadline | Status | Deadline | Actual deadline | Status | Deadline | Actual deadline | Status | PIC | Deadline | Actual deadline | Status | PIC | Deadline | Actual deadline | Status | PIC | Deadline | Actual deadline | Status
User site
Security & Compliance |  |  |  | Highest | All sprints |  |  |  |  | Not do |  |  | Not do |  |  | PC - eng | huynh.vu | 2025-11-14 |  | Done | nam.truong |  |  | Done
Multilang support |  |  |  | Highest | All sprints | File: Multiple language | Anh.nguyen75 | 2025-12-08 |  | In Progress |  |  | Not Start |  |  |  |  | 2025-12-12 |  | Todo | quang.do | 2025-12-12 |  | inprogress
[UC-C-00] Navigation Bar & Header |  |  |  | Medium | Sprint 1 |  | Long.ngo | 2025-10-31 | 2025-10-31 | Done | 2025-10-31 | 2025-10-31 | Done | [6 empty] | Todo | nam.truong | 2025-10-23 |  | Done
Landing Page | [UC-C-01] Landing Page |  | View landing page | Highest | Sprint 1 |  | Long.ngo | 2025-10-31 | 2025-10-31 | Done | 2025-11-04 | 2025-11-05 | In Review |  |  |  | quyet.nguyen4 | 2025-11-07 |  | Todo | thao.dong3 | 2025-11-07 |  | Ready for test
Authentication & KYC | [UC-C-02] Authentication | [UC-C-02.1] Log In | - User registration - Sumsub integration - Email verification | Highest | Sprint 1 |  | Mai.nguyen14 | 2025-10-31 | 2025-10-31 | In Review | 2025-11-04 | 2025-11-05 | In Review |  |  |  | quyet.nguyen4 | 2025-11-07 |  | Ready for test | tung.pham | 2025-11-07 |  | Ready for test
|  | [UC-C-02.2] Registration |  | Highest | Sprint 1 |  | Mai.nguyen14 |  |  | In Review |  |  | In Review |  |  |  | huynh.vu | 2025-11-07 |  | Ready for test | tung.pham | 2025-11-07 |  | Ready for test
Profile Management | [UC-S-01] Profile Management | [UC-S-01.1] View Profile | Allow startup to view their own profile | Highest | Sprint 1 |  | Mai.nguyen14 | 2025-11-05 | 2025-11-05 | In Review | 2025-11-07 | 2025-11-10 | In Review |  |  |  | huynh.vu | 2025-11-17 |  | inprogress | quang.do | 2025-11-20 |  | inprogress
|  | [UC-S-01.2] Edit Profile | Allow startup to edit their profile: - Business plans - Financial plans - Team information - Traction | Highest | Sprint 1 |  | Mai.nguyen14 | [9 empty] | huynh.vu | 2025-11-17 |  | inprogress | quang.do | 2025-11-21 |  | inprogress
|  | [UC-S-01.3] Profile Privacy Settings | Allow startup to block, restrict, or manage profile visibility and communications | Highest | Sprint 1 |  | Mai.nguyen14 | [9 empty] | huynh.vu | 2025-11-17 |  | inprogress | quang.do | 2025-11-21 |  | inprogress
| [UC-I-01] Profile Management | [UC-I-01.1] View Profile | Allow investor to view their own profile | Highest | Sprint 1 |  | Anh.nguyen75 | 2025-11-05 | 2025-11-05 | In Review | 2025-11-07 | 2025-11-07 | In Review |  |  |  | quyet.nguyen4 | 2025-11-17 |  | inprogress | quang.do, thao.dong3 | 2025-11-21 |  | inprogress
|  | [UC-I-01.2] Edit Profile | Allow investor to edit their profile: - investment thesis - portfolio - criteria | Highest | Sprint 1 |  | Anh.nguyen75 |  |  | In Review | [6 empty] | quyet.nguyen4 | 2025-11-17 |  | inprogress | thao.dong3 | 2025-11-21 |  | inprogress
|  | [UC-I-01.3] Profile Privacy Settings | Allow investor to block, restrict, or manage profile visibility and communications | Highest | Sprint 1 |  | Anh.nguyen75 |  |  | In Review | [6 empty] | quyet.nguyen4 | 2025-11-17 |  | inprogress | thao.dong3 | 2025-11-21 |  | inprogress
Dashboard | [UC-S-02] Startup Dashboard | [UC-S-02] Startup Dashboard | Allow investor to view dashboard on: - Upcoming calls or meetings with startups - Notifications on new connection requests - Charts showing engagement metrics (e.g., startups contacted, deals in each stage) | Highest | Sprint 3 |  | Anh.nguyen75 | 2025-12-09 |  | Not Start | 2025-12-10 |  | Not Start |  |  |  | quyet.nguyen4 | 2025-12-01 |  | Todo |  | 2025-12-03
| [UC-I-02] Investor Dashboard | [UC-I-02] Investor Dashboard | Allow investor to view dashboard on: - Upcoming calls or meetings with startups - Notifications on new connection requests - Charts showing engagement metrics (e.g., startups contacted, deals in each stage) | Highest | Sprint 3 |  | Mai.nguyen14 | 2025-12-09 |  | Not Start | 2025-12-10 |  | Not Start |  |  |  | quyet.nguyen4 | 2025-12-02 |  | Todo |  | 2025-12-05
Discovery | [UC-S-03] Investor Discovery | [UC-S-03.1]. Explore Start-ups | Allow startup to view the list of recommended matching investors | Highest | Sprint 2, Sprint 1 |  | Anh.nguyen75 | 2025-11-13 | 2025-11-13 | In Review | 2025-11-17 |  | In Progress |  |  |  | huynh.vu | 2025-11-19 |  | Todo | huy.du | 2025-11-25 |  | Todo
|  |  | Allow startup to filter investors by criteria such as sector, geography, investment stage, ticket size, and investor type (VC, angel, corporate, etc.). |  | Sprint 2, Sprint 1 | [11 empty] | huynh.vu | 2025-11-19 |  | Todo | huy.du | 2025-11-25 |  | Todo
|  | [UC-S-03.2]. View Start-ups Profile | Allow startup to view detailed investor profiles, including portfolio, investment thesis, focus sectors, average investment size, and team members. | Highest | Sprint 2 |  | Anh.nguyen75 | 2025-11-13 | 2025-11-13 | In Review | 2025-11-17 |  | In Progress |  |  |  | huynh.vu | 2025-11-19 |  | Todo | huy.du | 2025-11-25 |  | Todo
|  |  | Allow startup to send connection request to investor |  | Sprint 2 | [11 empty] | huynh.vu | 2025-11-19 |  | Todo | huy.du | 2025-11-25 |  | Todo
| [UC-I-03] Startup Discovery | [UC-I-03.1]. Explore Investor | Allow investor to view the list of recommended matching startups | Highest | Sprint 2, Sprint 1 |  | Mai.nguyen14 | 2025-11-13 | 2025-11-13 | In Review | 2025-11-17 |  | In Progress |  |  |  | huynh.vu | 2025-11-20 |  | Todo | huy.du | 2025-11-26 |  | Todo
|  |  | Allow investor to manually filter and search startups by criteria such as sector, location, stage, traction, and fundraising amount. |  | Sprint 1, Sprint 2 |  |  |  |  | In Review | [6 empty] | huynh.vu | 2025-11-20 |  | Todo | huy.du | 2025-11-26 |  | Todo
|  | [UC-I-03.2]. View Investor Profile | Allow investor to view detailed startup profiles, including: - business plan - traction - team - financials - fundraising information - performance report | Highest | Sprint 2 |  | Mai.nguyen14 | 2025-11-13 | 2025-11-13 | Not Start | 2025-11-17 |  | In Progress |  |  |  | huynh.vu | 2025-11-20 |  | Todo | huy.du | 2025-11-26 |  | Todo
|  |  | Allow investor to send a connection request to startups |  | Sprint 2 |  |  |  |  | Not Start | [6 empty] | huynh.vu | 2025-11-20 |  | Todo | huy.du | 2025-11-26 |  | Todo
Connection Management | [UC-S-04] Connection Management | [UC-S-04.1] Connection List |  | High | Sprint 2 |  | Anh.nguyen75 | 2025-11-13 | 2025-11-13 | In Review | 2025-11-19 |  | In Progress |  |  |  | quyet.nguyen4 | 2025-11-18 |  | Todo | dai.doan | 2025-11-25 |  | Todo
|  | [UC-S-04.2] Connection Details |  | High | Sprint 2 |  | Anh.nguyen75 | 2025-11-13 | 2025-11-13 | In Review | 2025-11-19 |  | In Progress |  |  |  | quyet.nguyen4 | 2025-11-19 |  | Todo | dai.doan | 2025-11-25 |  | Todo
| [UC-I-04] Connection Management | [UC-I-04.1] Connection List |  | High | Sprint 2 |  | Mai.nguyen14 | 2025-11-13 | 2025-11-13 | In Review | 2025-11-18 |  | In Progress |  |  |  | quyet.nguyen4 | 2025-11-18 |  | Todo | dai.doan | 2025-11-25 |  | Todo
|  | [UC-I-04.2] Connection Details |  | High | Sprint 2 |  | Mai.nguyen14 | 2025-11-13 | 2025-11-13 | In Review | 2025-11-18 |  | In Progress |  |  |  | quyet.nguyen4 | 2025-11-19 |  | Todo | dai.doan | 2025-11-25 |  | Todo
Deal Management & Docsend or Signit.sa Integration | [UC-S-05] Deal Room | [UC-S-05.1] Deal Room List |  | High | Sprint 2, Sprint 3 |  | Anh.nguyen75 | 2025-11-27 |  | Not Start |  |  | Not Start |  |  |  | huynh.vu | 2025-11-21 |  | Todo | thao.dong3 | 2025-11-24 |  | Todo
|  | [UC-S-05.2] Deal Room Details |  | High | Sprint 2, Sprint 3 |  | Anh.nguyen75 | 2025-11-27 |  | Not Start |  |  | Not Start |  |  |  | huynh.vu | 2025-11-24 |  | Todo | thao.dong3 | 2025-12-01 |  | Todo
| [UC-I-05] Deal Room | [UC-I-05.1] Deal Room List |  | Highest | Sprint 2, Sprint 3 |  | Mai.nguyen14 | 2025-11-27 |  | Not Start |  |  | Not Start |  |  |  | huynh.vu | 2025-11-24 |  | Todo | thao.dong3 | 2025-11-24 |  | Todo
|  | [UC-I-05.2] Deal Room Details |  | Highest | Sprint 2, Sprint 3 |  | Mai.nguyen14 | 2025-11-27 |  | Not Start |  |  | Not Start |  |  |  | huynh.vu | 2025-11-25 |  | Todo | thao.dong3 | 2025-12-01 |  | Todo
Performance Reporting Management | [UC-S-06] Performance Reporting | [UC-S-06] Performance Reporting |  | High | Sprint 3 |  | Long.ngo | 2025-11-26 |  | Not Start |  |  | Not Start |  |  |  | quyet.nguyen4 | 2025-12-04 |  | Todo | quang.do | 2025-12-10 |  | Todo
Content Management/ Educational Blog | [UC-C-03] Educational Blog | [UC-C-03.1] Blog List |  | Medium | Sprint 5 |  | Long.ngo |  |  | Not Start |  |  | Not Start | [6 empty] | Todo |  |  |  | Todo
|  | [UC-C-03.2] Blog Details |  | Medium | Sprint 5 |  | Long.ngo |  |  | Not Start |  |  | Not Start | [6 empty] | Todo |  |  |  | Todo
Messaging System | [UC-C-03] Messaging System | [UC-C-03.1] View Conversation List | Allow users (startup or investor) to view all active conversations sorted by most recent activity, showing name, profile, and last message preview. | High | Sprint 2 |  | Mai.nguyen14 | 2025-11-24 |  | Not Start | 2025-11-25 |  | Not Start | [6 empty] | Todo |  |  |  | Todo
|  | [UC-C-03.2] Message Details | Allow users to initiate a chat once a connection request has been accepted (either direction). | High | Sprint 2 |  | Mai.nguyen14 | 2025-11-24 |  | Not Start | 2025-11-26 |  | Not Start | [6 empty] | Todo |  |  |  | Todo
|  |  | Allow users to send and receive text messages in real time through integrated chat | [6 empty] | Not Start |  |  | Not Start | [6 empty] | Todo |  |  |  | Todo
Document Management | [M-UC-C-02] Document Management | [M-UC-C-02.1] Document List | Allow user to view a list of all documents they have uploaded, with details such as file name, upload date, and access status | Medium | Sprint 4 |  | Long.ngo |  |  | Not Start |  |  | Not Start | [6 empty] | Todo |  |  |  | Todo
|  |  | Allow user to upload documents (e.g., pitch deck, financial report, legal files) to the platform/delete uploaded documents |  | Sprint 4 |  |  |  |  | Not Start |  |  | Not Start | [6 empty] | Todo |  |  |  | Todo
|  |  | Allow user to set access permissions for each uploaded document — defining how long a document can be viewed |  | Sprint 4 |  |  |  |  | Not Start |  |  | Not Start | [6 empty] | Todo |  |  |  | Todo
|  | [M-UC-C-02.2] Document Details | Allow user to view document metadata and preview or download the file if access is granted. | Medium | Sprint 4 |  | Long.ngo |  |  | Not Start |  |  | Not Start | [6 empty] | Todo |  |  |  | Todo
Meeting Schedule Management |  |  |  | High | Sprint 3 |  | Long.ngo |  |  | Not Start |  |  | Not Start |  |  |  | quyet.nguyen4 | 2025-12-08 |  | Todo | quang.do | 2025-12-12 |  | Todo
WhatsApp Basic Integration | [UC-C-06] WhatsApp Reminders & Marketing | [UC-C-06.1] WhatsApp Reminders |  | Medium | Sprint 5 |  | Mai.nguyen14 |  |  | Not Start |  |  | Not Start | [6 empty] | Todo |  |  |  | Todo
|  | [UC-C-06.2] WhatsApp Automation Marketing |  | Medium | Sprint 5 |  | Mai.nguyen14 |  |  | Not Start |  |  | Not Start | [6 empty] | Todo |  |  |  | Todo
Matching System | [UC-C-07] Profile Matching Algorithm | [UC-C-07] Profile Matching Algorithm |  | Highest | Sprint 2, Sprint 3 |  | Mai.nguyen14 |  |  | Not do | 2025-11-28 |  | Not Start |  |  |  | huynh.vu |  |  | Todo |  |  |  | Todo | phong.vu |  |  | inprogress
Mobile App
Common |  |  | Setup source base | Highest | Sprint 1 |  |  |  |  | Not do |  |  | Not Start | [6 empty] | Todo | nam.truong |  |  | Done
[M-UC-C-00] Menu | [6 empty] | Anh.nguyen75
Authentication & KYC Integration | [M-UC-C-01] Authentication | [M-UC-C-01.1] Log In |  | Highest | Sprint 1 |  | Long.ngo |  |  | Not do | 2025-11-06 | 2025-11-07 | In Review | [6 empty] | Todo | nam.truong |  |  | Ready for test
|  | [M-UC-C-01.2] Registration |  | Highest | Sprint 1 |  | Long.ngo |  |  | Not do | 2025-11-06 | 2025-11-07 | In Review | [6 empty] | Todo | nam.truong |  |  | Ready for test
Dashboard | [M-S-02] Startup Dashboard | [M-S-02] Startup Dashboard |  | High | Sprint 3 |  | Anh.nguyen75 |  |  | Not do |  |  | Not Start |  |  |  | quyet.nguyen4 | 2025-12-01 |  | Todo | tung.pham | 2025-12-03 |  | Todo
| [M-I-02] Investor Dashboard | [M-I-02] Investor Dashboard |  | High | Sprint 3 |  | Mai.nguyen14 |  |  | Not do |  |  | Not Start |  |  |  | quyet.nguyen4 | 2025-12-02 |  | Todo | tung.pham | 2025-12-04 |  | Todo
Profile Management | [M-UC-I-01] Profile Management | [M-UC-I-01.1] View Profile |  | Highest | Sprint 2 |  | Long.ngo |  |  | Not do | 2025-11-18 |  | Not Start | [6 empty] | Todo | tung.pham | 2025-11-20 |  | inprogress
|  | [M-UC-I-01.2] Edit Profile |  | Highest | Sprint 2 |  | Long.ngo |  |  | Not do |  |  | Not Start | [6 empty] | Todo | tung.pham | 2025-11-20 |  | inprogress
|  | [M-UC-I-01.3] Profile Privacy Settings |  | Highest | Sprint 2 |  | Long.ngo |  |  | Not do |  |  | Not Start | [6 empty] | Todo | tung.pham | 2025-11-20 |  | inprogress
| [M-UC-S-01] Profile Management | [M-UC-S-01.1] View Profile |  | Highest | Sprint 2 |  | Long.ngo |  |  | Not do | 2025-11-20 |  | Not Start | [6 empty] | Todo | tung.pham | 2025-11-21 |  | inprogress
|  | [M-UC-S-01.2] Edit Profile |  | Highest | Sprint 2 |  | Long.ngo |  |  | Not do |  |  | Not Start | [6 empty] | Todo | tung.pham | 2025-11-21 |  | inprogress
|  | [M-UC-S-01.3] Profile Privacy Settings |  | Highest | Sprint 2 |  | Long.ngo |  |  | Not do |  |  | Not Start | [6 empty] | Todo | tung.pham | 2025-11-24 |  | inprogress
Discovery | [M-UC-I-03] Investor Discovery | [M-UC-I-03.1]. Explore Start-ups |  | High | Sprint 2 |  | Mai.nguyen14 |  |  | Not do | 2025-11-20 |  | Not Start | [6 empty] | Todo | nam.truong | 2025-11-24 |  | Todo
|  | [M-UC-I-03.3]. View Start-ups Profile |  | High | Sprint 2 |  | Mai.nguyen14 |  |  | Not do |  |  | Not Start | [6 empty] | Todo | nam.truong | 2025-11-25 |  | Todo
| [M-UC-S-03] Startup Discovery | [M-UC-S-03.1]. Explore Start-ups |  | High | Sprint 2 |  | Mai.nguyen14 |  |  | Not do | 2025-11-24 |  | Not Start | [6 empty] | Todo | nam.truong | 2025-11-26 |  | Todo
|  | [M-UC-S-03.3]. View Start-ups Profile |  | High | Sprint 2 |  | Mai.nguyen14 |  |  | Not do |  |  | Not Start | [6 empty] | Todo | nam.truong | 2025-11-27 |  | Todo
Connection Management | [M-UC-I-04] Connection Management | [M-UC-I-04.1] Connection List |  | High | Sprint 2 |  | Mai.nguyen14 |  |  | Not do | 2025-11-21 |  | Not Start | [6 empty] | Todo | nam.truong | 2025-11-25 |  | Todo
|  | [M-UC-I-04] Connection List |  | High | Sprint 2 |  | Mai.nguyen14 |  |  | Not do |  |  | Not Start | [6 empty] | Todo | nam.truong | 2025-11-25 |  | Todo
| [M-UC-S-04] Connection Management | [M-UC-S-04.1] Connection List |  | High | Sprint 2 |  | Anh.nguyen75 |  |  | Not do | 2025-11-25 |  | Not Start | [6 empty] | Todo | nam.truong | 2025-11-26 |  | Todo
|  | [M-UC-S-04] Connection List |  | High | Sprint 2 |  | Anh.nguyen75 |  |  | Not do |  |  | Not Start | [6 empty] | Todo | nam.truong | 2025-11-26 |  | Todo
Investment Process | [M-UC-I-05] Deal Room | [M-UC-I-05.1] Deal Room List |  | High | Sprint 3 |  | Mai.nguyen14 |  |  | Not do |  |  | Not Start |  |  |  | huynh.vu | 2025-11-21 |  | Todo | nam.truong | 2025-12-01 |  | Todo
|  | [M-UC-I-05.2] Deal Room Details |  | High | Sprint 3 |  | Mai.nguyen14 |  |  | Not do |  |  | Not Start |  |  |  | huynh.vu | 2025-11-24 |  | Todo | nam.truong | 2025-12-04 |  | Todo
| [M-UC-S-05] Deal Room | [M-UC-S-05.1] Deal Room List |  | High | Sprint 3 |  | Anh.nguyen75 |  |  | Not do |  |  | Not Start |  |  |  | huynh.vu | 2025-11-24 |  | Todo | nam.truong | 2025-12-01 |  | Todo
|  | [M-UC-S-05.2] Deal Room Details |  | High | Sprint 3 |  |  |  |  | Not do |  |  | Not Start |  |  |  | huynh.vu | 2025-11-25 |  | Todo | nam.truong | 2025-12-04 |  | Todo
| [M-UC-C-04] Meeting Schedule |  |  | High | Sprint 3 |  | Anh.nguyen75 |  |  | Not do |  |  | Not Start |  |  |  | huynh.vu | 2025-11-26 |  | Todo | nam.truong | 2025-12-04 |  | Todo
| Calendly Integration |  |  | High | Sprint 3 |  | Mai.nguyen14 |  |  | Not do |  |  | Not Start |  |  |  | huynh.vu | 2025-11-27 |  | Todo | nam.truong | 2025-12-04 |  | Todo
Chat Integration | [M-UC-C-02] Messaging System | [M-UC-C-02.1] View Conversation List |  | High | Sprint 3 |  | Mai.nguyen14 |  |  | Not do |  |  | Not Start |  |  |  | huynh.vu | 2025-12-03 |  | Todo | thao.dong3 | 2025-12-05 |  | Todo
|  | [M-UC-C-02.2] Message Details |  | High | Sprint 3 |  | Mai.nguyen14 |  |  | Not do |  |  | Not Start |  |  |  | huynh.vu | 2025-12-04 |  | Todo | thao.dong3 | 2025-12-09 |  | Todo
Document Sharing | [M-UC-C-03] Document Management | [M-UC-C-03.1] Document List |  | High | Sprint 4 |  | Mai.nguyen14 |  |  | Not do |  |  | Not Start | [6 empty] | Todo |  |  |  | Todo
|  | [M-UC-C-03.2] Document Deatails |  | High | Sprint 4 |  | Mai.nguyen14 |  |  | Not do |  |  | Not Start | [6 empty] | Todo |  |  |  | Todo
Push Notifications |  |  |  | Medium | Sprint 4 |  | Long.ngo |  |  | Not do |  |  | Not Start | [6 empty] | Todo |  |  |  | Todo
WhatsApp Integration |  |  |  | Medium | Sprint 4 |  | Long.ngo |  |  | Not do |  |  | Not Start | [6 empty] | Todo |  |  |  | Todo
Admin site
Authentication | [UC-AD-01] Authentication | [UC-AD-01] Authentication | Log In | Highest | Sprint 1 |  | Mai.nguyen14 | 2025-10-31 | 2025-10-31 | In Review | 2025-11-05 | 2025-11-05 | In Review | [6 empty] | Todo |  |  |  | Todo
Admin management | [UC-AD-02] Admin management | [UC-AD-02] Admin management |  | High | Sprint 2 |  | Mai.nguyen14 | 2025-10-31 | 2025-10-31 | In Review | 2025-11-05 | 2025-11-05 | In Review |  |  |  | quyet.nguyen4 | 2025-11-20 |  | Todo | huy.du | 2025-11-21 |  | inprogress
Admin Dashboard | [UC-AD-03] User Management | [UC-AD-03.1] User List | - view list user - Ban user - Unban user | High | Sprint 2 |  | Long.ngo | 2025-11-20 |  | In Progress | 2025-11-20 |  | Not Start |  |  |  | quyet.nguyen4 | 2025-11-21 |  | Todo | huy.du | 2025-11-25 |  | Todo
|  | [UC-AD-03.2] User Details | - view detail user | High | Sprint 2 |  | Long.ngo | 2025-11-20 |  | In Progress | 2025-11-24 |  | Not Start |  |  |  | quyet.nguyen4 | 2025-11-24 |  | Todo | huy.du | 2025-11-25 |  | Todo
|  | [UC-AD-03.3] KYC AI Screening Criteria | Approve Investor/Entrepreneur KYC | Highest | Sprint 2 |  | Long.ngo | 2025-11-20 |  | In Progress | 2025-11-21 |  | Not Start |  |  |  | huynh.vu | 2025-11-27 |  | Todo | huy.du | 2025-11-28 |  | Todo
| [UC-AD-04] Analytics Dashboard | [UC-AD-04] Analytics Dashboard | Analytics of which part? (Number of verify Investor/Entrepreneur, Number of submit KYC etc...) | High | Sprint 4 |  | Long.ngo | 2025-12-11 |  | Not Start | 2025-12-12 |  | Not Start |  |  |  | huynh.vu | 2025-12-09 |  | Todo | huy.du | 2025-12-11 |  | Todo
| [UC-AD-05] Deal Room Management | [UC-AD-05.1] Deal Room List | Admin Data Room Template Management | High | Sprint 3 |  | Long.ngo | 2025-12-08 |  | Not Start | 2025-12-10 |  | Not Start |  |  |  | huynh.vu | 2025-12-10 |  | Todo | huy.du | 2025-12-12 |  | Todo
|  | [UC-AD-05.2] Deal Room Details | Deal Room Dashboard | High | Sprint 3 |  | Long.ngo | 2025-12-08 |  | Not Start | 2025-12-10 |  | Not Start |  |  |  | quyet.nguyen4 | 2025-12-10 |  | Todo | huy.du | 2025-12-12 |  | Todo
CMS | [UC-AD-06] CMS |  | Create/Manage/Adjust Content | High | Sprint 4 |  | Long.ngo | 2025-11-24 |  | Not Start | 2025-11-25 |  | Not Start | [6 empty] | Todo |  |  |  | Todo

## Phase 1 - Master schedule
–– |  |  |  |  | Mobile không có wireframe dùng design của web | [14 empty] | 2 | [7 empty] | 3
Domain | Category | Module | Sub-features | UC | Task | Priority | Sprint | Note | BA Team | [10 empty] | BE team |  |  |  | FE team |  |  |  | Python Team
[9 empty] | Wireframe |  |  |  | Document |  |  |  | Design
[9 empty] | PIC | Deadline | Actual deadline | Status | Deadline | Actual deadline | Status | PIC | Deadline | Actual deadline | Status | PIC | Deadline | Actual deadline | Status | PIC | Deadline | Actual deadline | Status | PIC | Deadline | Actual deadline | Status
All sprint
Common | Project Foundation | Technical Discovery | CMS study
Tracking system study
Booking journey study
App platform assessment
Technical discovery meeting with Dengun, Must, and ARO
| Design System | Component Library | Build a shared library: Buttons, CTAs, Cards, Nav patterns, Footer.
Build UI modules: Booking/Enquiry modules, App download prompts, Mobile sticky CTAs.
| QA & Launch | Testing & Optimization | Cross-browser & Mobile QA (Chrome, Safari, Firefox; iOS, Android).
Performance (Lazy loading, page load speed) & SEO/Accessibility Hygiene.
|  | Go-Live | Support Production Deployment & handover Phase 2 roadmap documentation.
Sprint 1
camiral.com | Website UX/UI refresh | Homepage | Refresh content layout to balance golf, wellness, stay, real estate, and experiences.
Ryder cup lead Generation Form component
|  | Golf page | Ryder cup lead Generation Form component
Ryder cup lead Generation Form component
|  | Stay page | Add "Book a Stay" CTAs.
Improve the route into the Witbooking system.
Improve the mobile journey and tracking.
Cross-sell golf, wellness, dining, and experiences.
|  | Dining page | Replace generic buttons with dedicated enquiry CTAs.
|  | Wellness page | Add "Book Wellness" CTAs.
Improve the handoff to the OneJourney system.
Improve the content hierarchy and track CTA clicks.
Cross-link to stay and experiences.
|  | Real Estate page | Replace generic buttons with dedicated enquiry CTAs.
|  | Guest, member and resident pathways | Guest signposting
Member/resident signposting
|  | Experiences page | Reframe copy around lifestyle, wellness, gastronomy, and nature.
Implement cross-linking CTAs.
Ryder cup lead Generation Form component
|  | Newsletter Area | Ryder cup lead Generation Form component
|  | Ryder Cup 2031 Lead Generation Form | "Register Interest" form capturing name, email, country, and interest type.
Apply neutral compliance language (e.g., "Stay Updated").
|  | Role-based Popups/Call to action | Role: Guest CTAs
Role: Members/Residents CTAs
|  | Form | Test validation on desktop, mobile, and with long UTM URLs.
Confirm correct departmental routing.
Fix error messaging and thank-you states.
Track form starts, submissions, and errors.
|  | Menu Repair | Reduce friction in the mobile menu.
Reduce dependency on deep menu routes.
|  | CTA Standardization | Replace generic "Contact Us" labels with service-specific actions.
|  | Metadata Overhaul | Update metadata and SEO hygiene on changed pages where possible.
Title tags updated to reflect lifestyle and Ryder Cup positioning
| Booking Experience | Centralized Booking Hub | Create central "Book / Plan Your Visit" hub.
|  | Analytics | Track outbound booking clicks.
Mobile Redirect
Mobile sticky booking bar
Mobile CTAs
Web-to-app download banners
Quinta do Lago Resorts Gateway | Landing page | Master brand landing page development
Visual dual-routing portal to Algarve or Girona domains
Quinta do Lago Mobile App | UX/UI Update | Dashboard & Navigation Restructuring | Redesign the app home screen to show the most important buttons immediately without needing to scroll.
Personalized user greeting upon login
Comprehensive bottom navigation tab covering all core resort services
|  | Menu | Visual app menu utilizing icons and text hierarchy
|  | Wallet & Member Area | Wallet value proposition onboarding screen
Quick-access Member Area shortcut from the home view
|  | Service & Booking Fixes | Reorganized golf booking screen prioritizing booking options
Clean integrated booking webview hiding website navigation chrome
Dynamic section background hero imagery

## QC_Tracking PC WEB (hidden)
| USER | Design ENG | Design ARB | BE Status | FE Status | Testing PC ENG | Testing PC ARB | Testing % | Note | Count bug | Note issue
| [UC-C-00] Navigation Bar & Header | Done | Done | Done | Done | Done | Done | ENG: 97% ARB: 90% | ENG : % ARB : %
| [UC-C-01] Landing Page [UC-C-02] Authentication | Done | Done | Done | Done | Done | Done | ENG: 90% ARB: 90% | ENG: 90% ARB: 90% |  |  |  | Design | Design ARB | BE Status | FE Status | Testing
| [UC-S-01] Profile Management | Done | Done | Done | Done | Done | Done | ENG: 90% ARB: 90% | ENG: 90% ARB: 90% |  |  | User | 0 | 0 | 94.4444 | 94.4444
| [UC-I-01] Profile Management | Done | Done | Done | Done | Done | Done |  |  |  |  | Admin | 0 | N/A
| [UC-S-02] Startup Dashboard | Done | Done | Done | Done | Done | Done | ENG: 90% ARB: 90% | 26/12 -29/12
| [UC-I-02] Investor Dashboard | Done | Done | Done | Done | Done | Done |  | 26/12 -29/12
| [UC-S-03] Investor Discovery | Done | Done | Done | Done | Done | Done | ENG: 90% ARB: 90% | ENG: 90% ARB: 90%
| [UC-I-03] Startup Discovery | Done | Done | Done | Done | Done | Done
| [UC-S-04] Connection Management | Done | Done | Done | Done | Done | Done | ENG: 90% ARB: 90% | ENG: 90% ARB: 90%
| [UC-I-04] Connection Management | Done | Done | Done | Done | Done | Done
| [UC-S-05] Deal Room | Done | Done | Done | Done | Done | Done | ENG: 90% ARB: 90% | Start test 22/12 - 25/12
| [UC-I-05] Deal Room | Done | Done | Done | Done | Done | Done |  | Start test 22/12 - 25/12
| [UC-S-06] Performance Reporting | Done | Done | Done | Done | Done | Done | Eng 90% ARB: 90% | Start on 5/1 - 6/1
| [UC-I-06] Performance Reporting | Done | Done | Done | Done | Done | Done |  | Start on 5/1 - 6/1
| [UC-C-03] Educational Blog | Done | Done | Done | Done | Done | Done | ENG: 90% ARB: 90% | Start on 31/12 - 31/12
| [UC-C-03] Messaging System | Done | Done | Done | Done | Done | Done | ENG: 90% ARB: 90% | Start on 23/12 - 25/12
| [UC-C-07] Profile Matching Algorithm | N/A | N/A | Done | Done | Testing | N/A |  | Tạo sample + Testing on 22/12
| [UC-C-04] WhatsApp Reminders | Done | Done | Open | Open | Open | N/A |  | Start on 31/12 - 31/12
| [UC-C-08] Meeting Schedule | Done | Done | Done | Done | Done | N/A | Eng: 90% | Start on 23/12 - 25/12
[6 empty] | 80% | 80%
ADMIN
| [UC-AD-01] Authentication | Done | N/A | Done | Done | Done | N/A | 100% | 100%
| [UC-AD-02] Admin management | Done | N/A | Done | Done | Done | N/A | 100% | 100%
| [UC-AD-03] User Management | Done | N/A | Done | Done | Done | N/A | 100% | 100%
| [UC-AD-04] Analytics Dashboard | Done | N/A | Done | Done | Done | N/A | 85% | 30/12 - 31/12
| [UC-AD-05] Deal Room Management | Done | N/A | Done | Done | Done | N/A | 100% | 29/12 - 5/1
x | [UC-AD-06] CMS | N/A | N/A | Done | Done | N/A | N/A
Done

## QC_Tracking Mobile (hidden)
| Design ENG | BE Status | FE Status | Testing status | % IOS | % Android | Note | Count bug
[M-UC-C-01] Authentication | Done UI | Done | Done | Done | 100% | 100% |  |  |  | Design ENG | BE Status | FE Status | Testing status
[M-UC-I-01] Profile Management | Done UI | Done | Done | Done | 100% | 100% |  |  | User | 85.7143 | 85.7143 | 92.3077 | 0
[M-UC-S-01] Profile Management | Done UI | Done | Done | Done | 100% | 100%
[M-UC-S-03] Investor Discovery | Done UI | Done | Done | Done | 100% | 100%
[M-UC-I-03] Startup Discovery | Done UI | Done | Done | Done | 100% | 100%
[M-UC-I-04] Connection Management | Done UI | Done | Done | Done | 100% | 100%
[M-UC-S-04] Connection Management | Done UI | Done | Done | Done | 100% | 100%
[M-S-02] Startup Dashboard | Done UI | Done | Done | Done | 100% | 100%
[M-I-02] Investor Dashboard | Done UI | Done | Done | Done | 100% | 100%
[M-UC-I-05] Deal Room | Done UI | Done | Done | Done | 100% | 100%
[M-UC-S-05] Deal Room | Done UI | Done | Done | Done | 100% | 100%
[M-UC-C-04] Meeting Schedule | Done UI | Open | Open | Done | 100% | 100%
[M-UC-C-02] Messaging System | Done | Done | Done | Done | 100% | 100%
[UC-C-04] WhatsApp Reminders | Done | Open | Open | Open | 0% | 0% |  | Chưa có - 12/1 dev mới start
Push Notification | Done | Done | Done | Done | 100% | 100%
[5 empty] | 95% | 95%

## Nga_Tracking PC Responsive (hidden)
USER | Design link | Design ENG | Design ARB | BE Status | Mobile | FE Status | Testing status | % testing PC | Note | Time bàn giao cho QC
[UC-C-00] Navigation Bar & Header |  | Open | Open | Open | Open | Open | Open
[UC-C-01] Landing Page [UC-C-02] Authentication |  | Ready4Test | Ready4Test | Ready4Test | Ready4Test | Ready4Test | Testing | #REF!
[UC-S-01] Profile Management |  | Open | Open | Open | Open | Open | Open
[UC-I-01] Profile Management |  | Open | Open | Open | Open | Open | Open
[UC-S-02] Startup Dashboard |  | Open | Open | Open | Open | Open | Open
[UC-I-02] Investor Dashboard |  | Open | Open | Open | Open | Open | Open
[UC-S-03] Investor Discovery |  | Open | Open | Open | Open | Open | Open
[UC-I-03] Startup Discovery |  | Open | Open | Open | Open | Open | Open
[UC-S-04] Connection Management |  | Open | Open | Open | Open | Open | Open
[UC-I-04] Connection Management |  | Open | Open | Open | Open | Open | Open
[UC-S-05] Deal Room |  | Open | Open | Open | Open | Open | Open
[UC-I-05] Deal Room |  | Open | Open | Open | Open | Open | Open
[UC-S-06] Performance Reporting |  | Open | Open | Open | Open | Open | Open
[UC-C-03] Educational Blog |  | Open | Open | Open | Open | Open | Open
[UC-C-03] Messaging System |  | Open | Open | Open | Open | Open | Open
[M-UC-C-02] Document Management |  | Open | Open | Open | Open | Open | Open
[UC-C-06] WhatsApp Reminders & Marketing |  | Open | Open | Open | Open | Open | Open
ADMIN
[UC-AD-01] Authentication |  | Open | Open | Open | Open | Open | Open
[UC-AD-02] Admin management |  | Open | Open | Open | Open | Open | Open
[UC-AD-03] User Management |  | Open | Open | Open | Open | Open | Open
[UC-AD-04] Analytics Dashboard |  | Open | Open | Open | Open | Open | Open
[UC-AD-05] Deal Room Management |  | Open | Open | Open | Open | Open | Open
[UC-AD-06] CMS |  | Open | Open | Open | Open | Open | Open

## Sheet1 (hidden)
Epic | Task | Description | Milestone | Sprint | Epic | Task | Description
Common | Code base & project scaffolding |  | Milestone 1 | 1 | Common | Code base & project scaffolding | Base network, request, websocket connection Default IO & error handling
| Screen flows & navigation (app side) |  |  |  | Backend | s1: Support Windows and Ubuntu build | Infrastructure design, Terraform implementation Dockerization & image storage setup CI/CD pipeline
| Shared common components (app side) |  |  |  |  | s3: Account system (for Jorjin admin operators) | Create/read/update/delete account Activate and deactivate account by time and date Output the user's usage records, which can be used for statistics, or agora service usage and pricing, for example. Group & subgroup management GA4/GTM
| Base network, request, websocket connection |  |  |  | Base Core | Base Core | System Analysis System Design Base core Screen & logic navigation Camera system Handle input & interactive Input/Output system Pooling object system Base dialog system
| Default IO & error handling |  |  |  | Client Common | Layout-during login & setting
Backend | s1: Support Windows and Ubuntu build | Infrastructure design, Terraform implementation |  |  | Others | Handle glass and device
|  | Dockerization & image storage setup | Milestone 2 | 2 | Common | Screen flows & navigation (app side) | Sá»­ dá»¥ng Ä‘Æ°á»£c cÃ¡c tÃ­nh nÄƒng trong pháº§n main menu: Message, Log, Setting Táº¡o táº¥t cáº£ cÃ¡c layout sá»­ dá»¥ng trong project (chÆ°a bao gá»“m tÃ­nh nÄƒng)
|  | CI/CD pipeline |  |  | Backend | s4: Agora integration | Transcript for text log Chat room during remote assisting
| s2: Record messsage log and video streaming data | Persist livestream sesssion info into database |  |  | API & Socket Base | Socket Base | Api core Header and token manager Restful api manager Implement Socket library Handling keep alive Base socket Send/Receive request Handling reconnect socket
|  | Persist livestream video into file/object storage |  |  | Intergrate SDK | Intergrate SDK : Using JJSDK v. 2.x - Use J7EF-Plus SDK (JJSDK v.2.x) to develop the system. | Research JJSDK v. 2.x Android Library Importing Camera : Parameter Handler Camera : Frame Listener Camera : JJCamera Manager Sensor : JJDisplay Manager Sensor : Data Listener Handle Gesture
|  | Persist text message into database |  |  | AGORA SDK | AGORA SDK | Research Agora SDK Video Streaming intergation Voice Streaming intergation Video codec support h264, h265 Support Audio codec: AAC Need to support ON/OFF video and voice. (for example: voice chat only) internal webcam external UVC camera source Connect and re-connect Agora System
| s3: Account system (for Jorjin admin operators) | Create/read/update/delete account | Milestone 3 | 3 | Common | File sharing between clients(experties and engineers) Support PDF viewer inside the client platform | Sá»­ dá»¥ng Ä‘Æ°á»£c tÃ­nh nÄƒng screen sharing Sá»­ dá»¥ng Ä‘Æ°á»£c tÃ­nh nÄƒng PDF viewer sharing vÃ Ä‘á»“ng bá»™ vá»›i táº¥t cáº£ user
|  | Activate and deactivate account by time and date |  |  | Application | Whiteboard and Drawing Control | Whiteboard normal display Whiteboard from captured from shared screen (presentation, video) Intergrate painting Using socket to synchronize painting Erase painting Undo / Redo step Sizing change Color change HoÃ n thÃ nh tÃ­nh nÄƒng Whiteboard vÃ Ä‘á»“ng bá»™ vá»›i táº¥t cáº£ user Sá»­ dá»¥ng Ä‘Æ°á»£c chá»©c nÄƒng drawing control vÃ Ä‘á»“ng bá»™ vá»›i táº¥t cáº£ user
|  | Output the user's usage records, which can be used for statistics, or agora service usage and pricing, for example. |  |  | Backend | s5: Text message system | One-on-one message Group message API related text message service Integrate Rocketchat
|  | Group & subgroup management |  |  | Client Common | Streaming quality Account system Meeting room Menu Screen or window Sharing (common libs/base) Camera streaming Chatroom
|  | GA4/GTM |  |  |  |  | upload system(select, validate, error handling, notification); parse and loading .glb using sceneform; load models and error handling; model interaction (move, drag gestures); model interaction (rotation); model interaction (scaling, pinch-to-zoom gestures); optimize render and memory management;
| s4: Agora integration | Transcript for text log |  |  |  |  | Screen Sharing for windows platform; Screen sharing for Mobile platform; Camera streaming; Common & layout 3D Model File; Interaction; Additional from Menu : Log Page, Setting Page, Message Page; Application: Whiteboard normal display; Whiteboard from captured from shared screen (presentation, video); Intergrate painting; Using socket to synchronize painting; Erase painting; Undo / Redo step; Sizing change; Color change
|  | Chat room during remote assisting |  |  |  |  | Laser pointer & handle device: The laser pointer (Windows APP); Handle glass and device
| s5: Text message system | One-on-one message
Group message
API related text message service
Integrate Rocketchat
| Base Core | System Analysis
System Design
Base core
Screen & logic navigation
Camera system
Handle input & interactive
Input/Output system
Pooling object system
Base dialog system
| API & Socket Base | Api core
Header and token manager
Restful api manager
Implement Socket library
Handling keep alive
Base socket Send/Receive request
Handling reconnect socket
| Intergrate SDK : Using JJSDK v. 2.x - Use J7EF-Plus SDK (JJSDK v.2.x) to develop the system. | Research JJSDK v. 2.x
Android Library Importing
Camera : Parameter Handler
Camera : Frame Listener
Camera : JJCamera Manager
Sensor : JJDisplay Manager
Sensor : Data Listener
Handle Gesture
| AGORA SDK | Research Agora SDK
Video Streaming intergation
Voice Streaming intergation
Video codec support h264, h265
Support Audio codec: AAC
Need to support ON/OFF video and voice. (for example: voice chat only)
internal webcam
external UVC camera source
Connect and re-connect Agora System
| CLIENT COMMON | Streaming quality
Account system
Meeting room
Layout-during login & setting
Layout-during meeting
Menu
Screen or window Sharing (common libs/base)
Camera streaming
Chatroom
| APPLICATION | File sharing between clients(experties and engineers) Support PDF viewer inside the client platform
Screen Sharing for windows platform
Screen sharing for Mobile platform
Camera streaming
Common & layout 3D Model File
Interaction
Additional from Menu : - Log Page - Setting Page - Message Page
| Upload and handle 3D models | upload system(select, validate, error handling, notification)
parse and loading .glb using sceneform
load models and error handling
model interaction (move, drag gestures)
model interaction (rotation)
model interaction (scaling, pinch-to-zoom gestures)
optimize render and memory management
| Enable full 3D experience using JJSDK Switching between 3D and 2D scene based on AR glasses and platform <Moved to Phase 1> | integrate JJSDK for 3D uploaded model
AR 3D basics interation (move, rotate, scale)
Handle 3D and 2D scene switching based on AR glasses and apps platform
| Application | Whiteboard normal display
Whiteboard from captured from shared screen (presentation, video)
Intergrate painting
Using socket to synchronize painting
Erase painting
Undo / Redo step
Sizing change
Color change
| OTHERS | Handle glass and device
| PLATFORM AND DEVICE SUPPORTING | Android device w/ internal camera, Android OS 9 ~ Android 14
Android device w/ external UVC Camera, Android OS 9 ~ Android 14
Android device w/Type C, DP + Jorjin J7EF-Plus (UVC Camera)
Android tablet w/ internal camera, Android OS 9 ~ Android 14